## RSA tracker
Project | Ysgol Y Deri Expansion
Title: | Road Safety Audit (RSA) Desingers Response
Report Ref: | GS1077-2022 - Proposed Highways Works, Fort Road, Penarth - Stage 1 RSA - Final v1.docx
Date | 2022-01-05
Problem Ref | RSA observation | RSA recommendation | Design Team Response
1 | Location: Fort Road/ Lavernock Road junction. Summary: Insufficient intervisibility to/from the crossing point could increase the risk of vehicle collisions with pedestrians/cyclists. The intervisibility splays at the Fort Road/ Lavernock Road junction is considered to be insufficient between vehicles approaching the junction from Fort Road and the shared use crossing point (Ref: Photograph 1 on seperate tab). Restricted intervisibility at the crossing points could result in an increased risk of vehicle collisions with pedestrians/cyclists. | It is recommended that sufficient intervisibility splays be provided at the crossing point. | 1) The new works will include removing/translocating the hedgerow circled on the right hand side of the photo and installing a new footpath along right hand side to increase visibility here. 2) Our proposal under the S278 Fort Road widening works is to reduce the speed limits along Fort Road (for the seciton of the works) from 60mph to 30mph. 3) The vegetation on the left side will be cut back and maintianed by Council Maintenance hedge cutting team.
2 | Location: Fort Road/ Lavernock Road junction. Summary: Omission of tactile paving at the uncontrolled shared use crossing may result in an increased risk of vehicle collisions with pedestrians/cyclists. | It is recommended that tactile paving be provided at the uncontrolled crossing. | The drawing is to be updated to show the tactile paving
3 | Location: Lavernock Road – bus stops in close proximity of the site Summary: Omission of pedestrian crossing facilities may increase the risk of pedestrian trip hazards and pedestrian/vehicle collisions. | It is recommended that suitable pedestrian crossing facilities and boarding alighting area are provided on Lavernock Road in the vicinity of the bus stops. | The new ALN school and dropoff area has been included for parents and school minibus’within the site. It is not anticipated many, if any, of the pupils will be attending via the public bus network. It should be noted that there is no existing pedestrian refuge for passengers going north east, and the hedgerow has overgrown to the point where the north east bus stop is no longer visible.
4 | Location: Fort Road/ Lavernock Road junction and the proposed site access Summary: Vehicle encroachment by large vehicles could potentially resulting in head-on type or side impact type collisions. | It is recommended that the junction geometries are revised to address this problem | The Aecom tracking drawing tracks the vehicle through the centre of the widened Fort Rd, when it should be set to one of the running lanes. The road width used in the Aecom model is 5.5m, the scheme have widened the road to the required 6.1m. We propose to update the tracking drawing which will better represents the movement of a refuse vehicle.
5 | Location: Fort Road - proposed site access. Summary: Offset of site access gates from the edge of the carriageway could result in rear-end shunt or side impact type collisions | It is recommended that the gates are sufficiently off set from the edge of the carriageway to address this problem. | The gates are now set back to 6m as discussed with VoG Highways. 6m allows for cars to park to open gates without encroaching in Fort Rd

## Problem Location Plan
Location of identified problems

## Photo 1
Problem 1 Photograph